## Migration Plan
SQL Servers Migration to Azure Tasks (Lift & Shift Migration)
Pre-Migration Tasks
| Task No. | Task Name | Resources
| 1 | Identify the Servers to be Migrated | Vijay/Jakka
| 2 | Export the Dependency Analysis Information for servers from Movere | Jakka
| 3 | Export the Dependency Analysis Information for servers from Azure Migrate | Jakka
| 4 | Analyze the Server Dependencies Infromation | AMS Team
| 5 | Analyze the Server Dependencies Infromation | Jakka/Vijay
| 6 | Prepare the Master Servers Migration Sheet ( Include Azure IP and RG) | Vijay/Jakka
| 7 | Submit the Firewall Request | Vijay
| 8 | Deploy & Configure 2 Azure Migrate Appliances for Prod Subscription (1 for each VC) | Jakka
| 9 | Meet with Network Team to check if there are any Netwok BW Constaraints for Replication | Hector/Vijay/Jakka
| 10 | Prepare the Server for Migration | Jakka
| 11 | Start the Replaication | Jakka
| 12 | Copy the Required Software to Azure | Jakka/Chelo
Test Migration Plan
| Task No. | Task Name | Resources
| 1 | Create an Isolated VNET | Network Team
| 2 | Failover the VM's to the Isolated VNET (With out Impacting the Production VMs) | Jakka
| 3 | Validate the OS | Jakka
| 4 | Validate the Databases | Chelo
Full VM Miration Plan
| Task No. | Task Name | Resources
| 1 | Plan the Cut Over Date | Hector
| 2 | Open a Change Ticket | Ajay
| 3 | Disable the Monitoring | Jonathan
| 4 | Perform Full backup of the Server (On-Prem) | Ankit
| 5 | Failover the VM | Jakka
| 6 | OS Validation | Jakka
| 7 | Post Migration Tasks (Backup/Patching) | Jakka
| 8 | DB Validations | Chelo
| 9 | Apps Techinical Validation | AMS
| 10 | Run Test Cases | AMS
| 11 | Business users Validation
| 12 | Decom the on-Prem Servers (After 2 weeks of successful Migration) | Infra

## Inventory
SQLTSM01 | CCMS Vital | Server has RDMs
TSMMCPRDAPP02 | McAfee DB Server – Security
TSMMPRDAPP02 | Manage Engine Service Desk
TSMMPRDAPP03 | Serena
CSSVPRDIMG01 | Salus – Sidexis Application - Dental | Server is at Remote office.. Its on a Standalone host
TSMEDPPRDSAP02 | SAP Prod
TSMEDPQASAP03 | SAP QA | Win 2K3 Server
TSMEDPDEVSAP02 | SAP Dev | Win 2K3 Server
TSMCPRDSQL03 | iCES QNXT Prod
TSMCMTSTDEVSQL1 | CCMS Vital DEV
TSMCMODQASQL04 | iCES TSS QA
TSACESPRDSQL01 | iCES HealthSuite
TSACCPRDSQL01 | iCES
AHMMSSQL1 | TSA Multiple Applications DB Server | Physical Server
AHMMSDW | HealthSuite Datawarehouse
TSM-EDPSQL01 | Onbase
TSMEVPRDSQL01 | Enterprise Vault
TSMFPRDSQL01 | RightFax
TSMHTSPRDSQL01 | Not Found | Server not found
TSMOMODQADOD05 | DOD QA
TSMOMODQADOD06 | DOD QA
TSMPTSTDEVWEB01 | Web Portal
TSMQTSTDEVWEB02 | Web Portal
TSMRTSTDEVSQL01 | Acom3/Eligibility Test
TSSRTSTDEVSQL01 | MSP Test